## Test_Scenarios
Scenario_ID | Module | Scenario Description
SC001 | Login | Verify login with valid credentials
SC002 | Login | Verify error message with invalid credentials
SC003 | Cart | Add single product to cart
SC004 | Cart | Remove product from cart
SC005 | Payment | Successful payment with credit card
SC006 | Order | Place order and check confirmation message

## Test_Cases
TC_ID | Module | Test Case Description | Test Steps | Expected Result | Status | Actual Result
TC001 | Login | Login with valid credentials | 1. Go to login page 2. Enter valid credentials 3. Click Login | User should be logged in successfully | Fail | User unable login
TC002 | Login | Login with invalid credentials | 1. Go to login page 2. Enter invalid credentials 3. Click Login | Error message should be displayed | Pass | Error message shown for invalid login
TC003 | Cart | Add single product to cart | 1. Go to product page 2. Click 'Add to cart' | Product should be added to cart | Fail | Product added, but total was incorrect
TC004 | Cart | Remove product from cart | 1. Go to cart 2. Click remove icon on product | Product should be removed from cart | Pass | Product removed from cart
TC005 | Payment | Make payment with valid card | 1. Go to checkout 2. Enter valid card details 3. Submit payment | Payment should be successful | Pass | Payment completed successfully
TC006 | Order | Place order after successful payment | 1. Add items to cart 2. Proceed to checkout 3. Complete payment 4. Confirm order | Order should be placed and confirmation shown | Pass | Order confirmation message displayed

## Bug_Reports
Bug ID | Title | Steps to Reproduce | Severity | Priority | Status | Reported By
BUG001 | Login button not responsive | 1. Go to login page 2. Enter credentials 3. Click Login button (no action) | High | High | Open | Harshitha
BUG002 | Incorrect cart total | 1. Add single product to cart 2. Go to cart page | Medium | Medium | In Progress | Harshitha

## Test_Plan
Section | Details
Project Name | ShopEasy – E-commerce Website
Scope | To validate all functional modules like login, cart, checkout, and payment
Test Types | Smoke Testing, Functional Testing, Regression Testing
Test Tools | Excel, Jira (if available)
Test Deliverables | Test Scenarios, Test Cases, Bug Reports, Test Summary